## Sheet1
# | Risk | Risk Owner | Probability | Impact (weeks) | Risk Exposure (weeks)
E.g. | IF customer design approval is more than 1 month late, THEN software implementation will be delayed leading to a day for day schedule slip | The Agency | 0.4 | 2 | 0.8
1 | Problems migrating data from the old database |  | 0.2
2 | Security exploint found in API |  | 0.4
3 | Scope change |  | 0.2
4 | government shut down
5 | 6 month warrenty not long enough
6
7
8
9
10